## Slide 1: Chapter 7: Project Cost Management
Information Technology Project Management, Ninth Edition
Note: See the text itself for full citations

## Slide 2: HOW MUCH COST MANAGEMENT should there be on a project
What is Cost Management in Project Management?
Cost management is the process of
Estimating, predicting, allocating, reduce budget overrun,
Realistic budget, satisfying stakeholders., and controlling project costs
Projected costs are calculated during the planning phase of a project and must be approved before work begins
Usually measured in monetary units like dollars that must be paid to acquire goods and services

## Slide 3: COST MANAGEMENT should there be on a project
What is Cost Management in Project Management?
  Process of estimating, allocating, and controlling project costs
  Process which allows a business to predict future expenses
Why is cost management important in project management?
  vital to an organization’s project planning process and estimating (hiring,
  materials, renovations, new labs, etc..)
What are the benefits of cost management in project management?
    Prevents overrun and overspending, avoid risks
What are the challenges of cost management?
    Lack of resources, Inaccurate estimation, Outdated tools
Who is responsible for cost management in a project?
  Project managers. As part of their role, they must estimate total costs, plan the budget, monitor spend, and prepare for potential risks.
Which project tools help with cost management in project management?
Reporting, accurate budgeting

## Slide 4: Learning Objectives (1 of 2) HOW MUCH COST MANAGEMENT should there be on a project
Develop a justification for project cost management and its importance in achieving project success
Explain basic project cost management principles, concepts, and terms
Describe the process of planning cost management
Discuss different types of cost estimates and methods for preparing them
Using an example of an information technology (IT) project, list and describe the processes of determining a budget and preparing a cost estimate. Discuss different types of cost estimates and methods for preparing them

## Slide 5: Learning Objectives (2 of 2)
Justify the use of earned value management and project portfolio management to assist in cost control
Describe how project management software can assist in project cost management
Discuss considerations for agile/adaptive environments

## Slide 6: The Importance of Project Cost Management
IT projects have a poor track record for meeting budget goals
A cost overrun is the additional percentage or dollar amount by which actual costs exceed estimates
A 2019 Harvard Business Review study reported an average cost overrun of 27 percent. The most important finding was the discovery of a large number of gigantic overages or “black swans”

## Slide 7: What Went Wrong?
The United Kingdom’s National Health Service IT modernization program was called the greatest IT disaster in history with an estimated $26 billion overrun
The program had problems due to incompatible systems, resistance from physicians, and arguments among contractors about who’s responsible for what
It was finally scrapped in 2011.

## Slide 8: Project Cost Management Processes: 4 Proc.
Planning cost management :determining the policies, procedures, and documentation that will be used for planning, executing, and controlling project cost.
Estimating costs: developing an approximation or estimate of the costs of the resources needed to complete a project
Determining the budget: allocating the overall cost estimate to individual work items to establish a baseline for measuring performance
Controlling costs: controlling changes to the project budget (cost forecasts, asset update, change requests)

## Slide 9: What is Project Cost Management?

## Slide 10: How Do We Manage Cost?
Processes
  Planning cost management
  Estimate Costs
  Determine Budget
  Control Costs
Estimate
Costs
Determine Budget
Control
Costs
Planning cost management

## Slide 11: Types of Costs and Benefits
Tangible costs or benefits are those costs or benefits that an organization can easily measure in dollars
Measure them accurately.
(hard cost) Cost you can “see feel and touch”. Ex: purchase cost of computer, power usage software purchase costs, wages, labor
Intangible costs or benefits are costs or benefits that are difficult to measure in monetary terms.
Cannot measure accurately
(soft costs). Costs cannot “see, feel or touch”. Ex. Productivity gains from computer use, sales gains from a better customer support, etc. (Employee moral)

## Slide 12: Basic Principles of Cost Management
Most members of an executive board better understand and are more interested in financial terms than IT terms , so IT project managers must speak their language
  Profits are revenues minus expenditures
  Profit margin is the ratio of revenues to profits
  Life cycle costing considers the total cost of ownership, or development plus support costs, for a project
  Cash flow analysis determines the estimated annual costs and benefits for a project and the resulting annual cash flow

## Slide 13: Types of Costs and Benefits
Direct costs are costs that can be directly related to producing the products and services of the project. Produce goods or services (good sold, unsold), raw material, labor
Indirect costs are costs that are not directly related to the products or services of the project, but are indirectly related to performing the project.
Cost that affect the entire company, not just the product. Ex: advertising, depreciation, accounting services
Called overhead, nor related for making the product. In general, they are fixed. Ex. Pay the rent of the building or variables, pay the electricity, water bills
Sunk cost is money that has been spent in the past; when deciding what projects to invest in or continue, you should not include sunk costs.
Expenses have already occurred and can’t be changed or avoided or recovered.

## Slide 14: More Basic Principles of Cost Management
Learning curve theory states that when many items are produced repetitively, the unit cost of those items decreases in a regular pattern as more units are produced
Reserves are dollars included in a cost estimate to mitigate cost risk by allowing for future situations that are difficult to predict
  Contingency reserves allow for future situations that may be partially planned for (sometimes called known unknowns) and are included in the project cost baseline
  Management reserves allow for future situations that are unpredictable (sometimes called unknown unknowns)

## Slide 15: How Do We Manage Cost?
Processes
  Planning cost management
  Estimate Costs
  Determine Budget
  Control Costs
Estimate
Costs
Determine Budget
Control
Costs
Planning cost management

## Slide 16: Planning Cost Management
The first step in project cost management is planning how the costs will be managed throughout the life of the project
  The project team uses expert judgment, analytical techniques, and meetings to develop the cost management plan
Cost management plan includes:
  Level of accuracy
  Units of measure
  Organizational procedure links
  Control thresholds
  Rules of performance measurement
  Reporting formats
  Process descriptions

## Slide 17: How Do We Manage Cost?
Processes
  Planning cost management
  Estimate Costs
  Determine Budget
  Control Costs
Estimate
Costs
Determine Budget
Control
Costs
Planning cost management

## Slide 18: Estimating Costs (1 of 4)
Project managers must take cost estimates seriously if they want to complete projects within budget constraints
  Types of cost estimates
  Tools and techniques for estimating costs
  Typical problems associated with IT cost estimates

## Slide 19: Estimating Costs (2 of 4)
Type of Estimate | When Done | Why Done | Typical Range
Rough order of magnitude (ROM) | Very early in the project life cycle, often 3–5 years before project completion | Provides estimate of cost for selection decisions | -50% to + 100%
Budgetary | Early, 1–2 years out | Puts dollars in the budget plans | -10% to +25%
Definitive | Later in the project, less than 1 year out | Puts dollars in the budget plans | -5% to +10%
Table 7-1 Types of cost estimates

## Slide 20: Estimating Costs (3 of 4)
The number and type of cost estimates vary by application area
  The Association for the Advancement of Cost Engineering International identifies five types of cost estimates for construction projects
    Order of magnitude, conceptual, preliminary, definitive, and control
  Estimates are usually done at various stages of a project
    Should become more accurate as time progresses
  It is important to provide supporting details for estimates and updates to project documents
  A large percentage of total project costs are often labor costs

## Slide 21: Estimating Costs (4 of 4)
Department | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Totals
Information systems | 24 | 31 | 35 | 13 | 13 | 116
Marketing systems | 3 | 3 | 3 | 3 | 3 | 15
Reservations | 12 | 29 | 33 | 9 | 7 | 90
Contractors | 2 | 3 | 1 | 0 | 0 | 6
Totals | 41 | 66 | 72 | 25 | 23 | 227
Table 7-2 Maximum FTE by department by year

## Slide 22: Cost Estimation Tools and Techniques
Analogous or top-down estimates
  Use the actual cost of a previous, similar project as the basis for estimating the cost of the current project
Bottom-up estimates
  Involve estimating individual work items or activities and summing them to get a project total
Three-point estimates
  Involve estimating the most likely, optimistic, and pessimistic costs for items
Parametric estimating
  Uses project characteristics (parameters) in a mathematical model to estimate project costs

## Slide 23: Typical Problems with IT Cost Estimates
Reasons for inaccuracies
  Estimates are done too quickly
  People lack estimating experience
  Human beings are biased toward underestimation
  Management desires accuracy

## Slide 24: How to Develop a Cost Estimate and Basis of Estimates (1 of 3)
See the text for a detailed example of creating a cost estimate for the Surveyor Pro project described in the opening case
  Before creating an estimate gather as much information as possible about the project, ask how the organization plans to use the cost estimate, and clarify the ground rules and assumptions

## Slide 25: How to Develop a Cost Estimate and Basis of Estimates (2 of 3)
Notes: .

## Slide 26: How to Develop a Cost Estimate and Basis of Estimates (3 of 3)

## Slide 27: How Do We Manage Cost?
Processes
  Planning cost management
  Estimate Costs
  Determine Budget
  Control Costs
Estimate
Costs
Determine Budget
Control
Costs
Planning cost management

## Slide 28: Determining the Budget (1 of 2)
Budgeting involves allocating the project cost estimate to individual work items over time
  Material resources or work items are based on the activities in the WBS for the project
Important goal is to produce a cost baseline
  Time-phased budget that project managers use to measure and monitor cost performance

## Slide 29: Determining the Budget (2 of 2)

## Slide 30: How Do We Manage Cost?
Processes
  Planning cost management
  Estimate Costs
  Determine Budget
  Control Costs
Estimate
Costs
Determine Budget
Control
Costs
Planning cost management

## Slide 31: Controlling Costs
Activities involved in controlling project costs
  Monitoring cost performance
  Ensuring that only appropriate project changes are included in a revised cost baseline
  Informing project stakeholders of authorized changes to the project that will affect costs
Several tools and techniques assist in project cost control
  Expert judgment, data analysis, project management information systems, and the to-complete performance index

## Slide 32: Earned Value Management (EVM) (1 of 5)
Project performance measurement technique that integrates scope, time, and cost data
  Given a baseline (original plan plus approved changes), you can determine how well the project is meeting scope, time, and cost goals
Earned value management involves calculating three values for each activity or summary activity from a project’s WBS
  Planned value
  Actual cost
  Earned value

## Slide 33: Earned Value Management (EVM) (2 of 5)
Activity | Week 1
Earned value (EV) | 5,000
Planned value (PV) | 10,000
Actual cost (AC) | 15,000
Cost variance (CV) | -10,000
Schedule variance (SV) | -5,000
Cost performance index (CPI) | 33%
Schedule performance index (SPI) | 50%
Table 7-3 Earned value calculations for one activity after week 1

## Slide 34: Earned Value Management (EVM) (3 of 5)
Term | Formula
Earned value (EV) | EV = PV of all completed work
Cost variance (CV) | CV = EV - AC
Schedule variance (SV) | SV = EV - PV
Cost performance index (CPI) | CPI = EV/AC
Schedule performance index (SPI) | SPI = EV/PV
Estimate at completion (EAC) | EAC = BAC/CPI
Estimated to Complete (ETC) | ETC = EAC - AC
Table 7-4 Earned value formulas

## Slide 35: Earned Value Management (EVM) (4 of 5)
Important concepts
  Cost variance (CV) is the earned value minus the actual cost
  Schedule variance (SV) is the earned value minus the planned value
  Cost performance index (CPI) is the ratio of earned value to actual cost
  Schedule performance index (SPI) is the ratio of earned value to planned value
  Estimate at completion (EAC) is an estimated cost of completing a project based on performance to date
  To-complete performance index (TCPI) is a measure of the cost performance that must be achieved with the remaining resources to meet a specific goal

## Slide 36: Earned Value Management (EVM) (5 of 5)

## Slide 37: Global Issues (1 of 2)
EVM is used worldwide, and it is particularly popular in the Middle East, South Asia, Canada, and Europe
  Most countries require EVM for large defense or government projects, as shown in Figure 7-7
  EVM is also used in such private-industry sectors as IT, construction, energy, and manufacturing.
    However, most private companies have not yet applied EVM to their projects because management does not require it, feeling it is too complex and not cost effective

## Slide 38: Global Issues (2 of 2)

## Slide 39: Project Portfolio Management
Many organizations collect and control an entire suite of projects or investments as one set of interrelated activities in a portfolio
Five levels for project portfolio management
  Put all your projects in one database
  Prioritize the projects in your database
  Divide your projects into two or three budgets based on type of investment
  Automate the repository
  Apply modern portfolio theory, including risk-return tools that map project risk on a curve

## Slide 40: Using Project Management Software to Assist in Project Cost Management (1 of 2)
Spreadsheets are a common tool for resource planning, cost estimating, cost budgeting, and cost control
  Many companies use more sophisticated and centralized financial applications software for cost information
Project management software can increase a project manager’s effectiveness during each process of project cost management
  Many IT project managers use other tools to manage cost information because they do not know that they can use project management software, or they do not track costs based on a WBS, as most project management software does

## Slide 41: Using Project Management Software to Assist in Project Cost Management (2 of 2)
Recent Studies on PPM Software
  2017 Gartner report says the market continues to grow, with annual sales over $2.3 billion
  Forrester estimates ROIs of 250 percent from PPM tools
  Pfizer and Ford use PPM software to improve transparency of the many projects they manage

## Slide 42: Considerations for Agile/Adaptive Environments
AgileEVM is an adapted implementation of EVM
  Uses the Scrum framework artifacts as inputs, uses traditional EVM calculations, and is expressed in traditional EVM metrics
  Requires a minimal set of input parameters
    Actual cost of a project, an estimated product backlog, a release plan that provides information on the number of iterations in the release and the assumed velocity
  All estimates can be in hours, story-points, team days or any other consistent estimate of size
    The critical factor is that it must be a numerical estimate of some kind

## Slide 43: Chapter Summary
Project cost management is a traditionally weak area of IT projects
  Project managers must understand several basic principles of cost management to be effective in managing project costs
Main processes
  Plan cost management
  Estimate costs
  Determine the budget
  Control costs
Several software products can assist with project cost management